| **Project Task** | **Duration** | **Start** | **Finish** | **Resources** |
| --- | --- | --- | --- | --- |
| **Project Planning**  Submit Additional Data Sets  Review & Recommend Data Set  Select Categories & Variables  Develop Research Topic  Review Research Topic  Create Work Plan  Create Project Folders in Github  Project Plan Uploaded to Github | 5 days | 9/26/17 | 10/2/17 | Zac, Anwar  David  Zach  Team  Team  Zac, Yvonne  Tyler  Tyler |
| **Data Preparation & Documentation**  Data Set Description  Intellectual Property Constraints  Metadata Description  Preliminary Data Analysis  Preliminary Data Cleaning Guidelines  Data Cleaning  Compile Data Cleaning Documentation  Data Documentation Uploaded to Github | 21 days | 10/2/17 | 10/25/17 | Zac  Tyler  Anwar  Team  Yvonne  Team  Team  Tyler |
| **Weekly Team Meetings** |  | 9/30/17 | 12/2/17 | Team |
| **Team Progress Meeting** | .5 day | 10/31/17 | 10/31/17 | David, Team |
| **R Script Draft**  Draft R Script  R Script Uploaded to Github | 12 days | 11/1/17 | 11/13/17 | Zac, Yvonne, Team Ty |
| **R Plot Draft**  Draft R Plot  R Plot Uploaded to Github | 7 days | 11/14/17 | 11/21/17 | Zac, Yvonne, Team Ty |
| **Project Presentation**  Prepare Presentation  Make Presentation | 11 days | 11/21/17 | 12/5/17 | Team Team |
| **Git Package** |  | 12/5/17 | 12/5/17 |  |